## Sheet1
Risk | Risk Statement | Response Strategy | Objectives | Likelihood | Impact | Risk Level
Internet (wi-fi) down | The wifi connection in my flat could potentially go down. This means I would not be able to access resources on it. | Use neighbour's wifi or go over to my parents' house and use theirs. | Make sure there are back up options to gain access to the internet. | low | medium | 4
Theft | If my flat is broken into and my possesions are stolen, it would stop me from being able to work on the project unless I could use someone else's devices. | Ensure the flat is locked whenever I am out and ask family if I could use/borrow their devices. | Make sure there are no easy opportunites for my flat to be broken into and have back up options. | low | high | 7
Running out of time | The project could take longer than I am expecting and I am unable to finish everything on time. | Stick with what is on the Jira board in order to reach the MVP target. Ask for help, if it is necessary, from the trainer. | Maintain good project and time management. | low | high | 7
Laptop dies | The battery or something else on my laptop could cause it to stop working. | Use my older laptop and get everything set up on there to use instead. | Make sure to push regularly to GitHub when working on the project and have my older laptop ready to go. | low | medium | 4
Illness | I could become ill and find it more difficult to complete the project. | Follow good hygiene, do not come into close contact with sick people. | Make sure I don't become so sick that I cannot work on my project. | low | meduim | 4
Deliveries | Someone could deliver something to my flat which will take me away from working on my project. | Be as quick as possible when anwering the door. Don't let it distract you too much from the project. | Keep focused on the project. | high | low | 3
Impact
|  |  |  | Low | Medium | High
|  | Likelihood | Low | 1 | 4 | 7
|  |  | Medium | 2 | 5 | 8
|  |  | High | 3 | 6 | 9